## Sheet1
IndusMach Industries - Risk Treatment Plan
Treatment ID | Risk ID | Option | Mitigation Strategy / Action | Resource Required | Estimated Cost ($) | Target Date | Residual Risk Level
TRT-001 | RSK-OT-001 | Accept (Temporary) + Compensating Controls | Deploy FortiGate Industrial DMZ Firewall micro-segmentation, USB lockout, Read-Only Historian Relay, and defer patch to Q4 Overhaul. | OT Security & Control Eng | 25000 | 2026-11-30 | Medium
TRT-002 | RSK-OT-003 | Mitigate | Deploy Claroty Secure Remote Access (SRA) with MFA, jump hosts, and session recording. | IT/OT Infra Team | 45000 | 2026-09-01 | Low
TRT-003 | RSK-IT-001 | Mitigate | Deploy Microsegmentation, EDR expansion, and Immutable Veeam Cloud Backups. | Enterprise IT Team | 80000 | 2026-09-30 | Low