## Sheet1
IndusMach Industries - IT/OT Change Management Register (20 Changes)
Change ID | System / Asset ID | Factory ID | Change Description | Business Impact | Security Impact | Associated Risk ID | Testing Completed? | CAB Approval Status | Maintenance Window Scheduled | Rollback Plan Documented? | Execution Result
CHG-001 | AST-IT-001 | FAC-PUN | Firmware upgrade & security patch deployment for AST-IT-001 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-IT-002 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-002 | AST-OT-002 | FAC-NAG | Firmware upgrade & security patch deployment for AST-OT-002 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-OT-003 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-003 | AST-IT-003 | FAC-CHE | Firmware upgrade & security patch deployment for AST-IT-003 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-IT-004 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-004 | AST-OT-004 | FAC-BLR | Firmware upgrade & security patch deployment for AST-OT-004 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-OT-005 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-005 | AST-IT-005 | FAC-AMD | Firmware upgrade & security patch deployment for AST-IT-005 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-IT-006 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-006 | AST-OT-006 | FAC-HYD | Firmware upgrade & security patch deployment for AST-OT-006 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-OT-007 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-007 | AST-IT-007 | FAC-PUN | Firmware upgrade & security patch deployment for AST-IT-007 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-IT-008 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-008 | AST-OT-008 | FAC-NAG | Firmware upgrade & security patch deployment for AST-OT-008 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-OT-009 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-009 | AST-IT-009 | FAC-CHE | Firmware upgrade & security patch deployment for AST-IT-009 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-IT-010 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-010 | AST-OT-010 | FAC-BLR | Firmware upgrade & security patch deployment for AST-OT-010 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-OT-011 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-011 | AST-IT-011 | FAC-AMD | Firmware upgrade & security patch deployment for AST-IT-011 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-IT-012 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-012 | AST-OT-012 | FAC-HYD | Firmware upgrade & security patch deployment for AST-OT-012 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-OT-013 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-013 | AST-IT-013 | FAC-PUN | Firmware upgrade & security patch deployment for AST-IT-013 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-IT-014 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-014 | AST-OT-014 | FAC-NAG | Firmware upgrade & security patch deployment for AST-OT-014 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-OT-015 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-015 | AST-IT-015 | FAC-CHE | Firmware upgrade & security patch deployment for AST-IT-015 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-IT-016 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-016 | AST-OT-016 | FAC-BLR | Firmware upgrade & security patch deployment for AST-OT-016 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-OT-017 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-017 | AST-IT-017 | FAC-AMD | Firmware upgrade & security patch deployment for AST-IT-017 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-IT-018 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-018 | AST-OT-018 | FAC-HYD | Firmware upgrade & security patch deployment for AST-OT-018 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-OT-019 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-019 | AST-IT-019 | FAC-PUN | Firmware upgrade & security patch deployment for AST-IT-019 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-IT-020 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful
CHG-020 | AST-OT-020 | FAC-NAG | Firmware upgrade & security patch deployment for AST-OT-020 during maintenance window. | Low - Scheduled during planned 4-hour plant stoppage. | High Positive - Mitigates critical CVSS vulnerabilities. | RSK-OT-001 | Yes (Passed in Staging Lab) | Approved by IT/OT CAB | 2026-08-20 02:00 AM | Yes (Full Image Backup) | Successful