## Sheet1
IndusMach Industries - Master Internal Audit Findings (30 Findings)
Finding ID | Audit Area | Criteria (Policy / Standard) | Condition (Observed Gap) | Root Cause | Consequence / Business Impact | Associated Risk ID | Severity | Audit Recommendation | Management Response & Action Plan | Assigned Owner | Target Due Date | Closure Status
AUD-001 | OT Network Segmentation | IEC 62443-3-3 SR 5.1 | Direct unauthenticated RDP route permitted from Corporate IT to Pune SCADA HMI. | Legacy firewall rule left active without IDMZ jump host routing. | Potential lateral movement of corporate malware directly into factory SCADA. | RSK-OT-002 | Critical | Remove direct RDP firewall rule; enforce Claroty SRA Jump Host with MFA. | Management agrees; firewall team will remove direct route by Aug 31. | Network Security Lead | 2026-08-31 | In Progress
AUD-002 | Unpatched Legacy OS Machine | NIST SP 800-82 Rev 3 §6.2 | Windows 7 Embedded operating system on Pune Gear Shaping Machine lacks MS17-010 patch. | Machine cannot be upgraded without replacing physical CNC controller hardware ($1.2M cost). | Exposes Line A to EternalBlue ransomware propagation. | RSK-OT-001 | Critical | Implement IDMZ micro-segmentation, USB lockout, and schedule upgrade during Q4 overhaul. | Management accepts temporary risk under RA-2026-001; compensating controls deployed. | Pune Plant Manager & OT Lead | 2026-11-30 | Risk Accepted
AUD-003 | Vendor Remote Access Governance | ISO 27001:2022 A.5.19 | Third-party vendors accessing factory PLCs via unmonitored legacy SSL VPN without MFA. | Contract agreements lacked mandatory MFA and session recording requirements. | Unauthorized vendor access or credential theft leading to undetected PLC manipulation. | RSK-OT-003 | Critical | Mandate Claroty SRA jump-host portal with Duo MFA and full session recording. | Deploying Claroty SRA portal across all 6 plants; completion targeted Sept 15. | Third-Party Risk Manager | 2026-09-15 | In Progress
AUD-004 | Dormant Privileged Accounts | NIST CSF PR.AC-1 | 12 Active Directory domain admin accounts inactive for >90 days without deactivation. | Lack of automated identity lifecycle reconciliation between HR and AD. | Increased attack surface for brute-force credential stuffing attacks. | RSK-IT-003 | High | Disable dormant accounts immediately and implement automated 90-day AD cleanup script. | Accounts disabled immediately; automated cleanup script deployed in staging. | IAM Operations Lead | 2026-08-20 | Closed
AUD-005 | Unrestricted USB Devices on EWS | NIST SP 800-82 Rev 3 §6.4 | Engineering Workstations in Nagpur Plant allow read/write access to unverified personal USB drives. | Group Policy USB block not linked to local plant Active Directory OUs. | High risk of malware infection (e.g., Stuxnet/W32.Shty) via technician USB drives. | RSK-OT-006 | High | Enforce physical port locks and GPO USB block; install optical USB scan kiosk. | Installing physical USB locks; GPO updated across all plant OUs. | Plant IT Supervisor | 2026-08-30 | In Progress
AUD-006 | OT Network Segmentation | IEC 62443-3-3 SR 5.1 | Direct RDP connection permitted from Corporate IT laptop to Level 2 WinCC SCADA HMI in Pune Plant. | Legacy firewall rule left active without IDMZ jump host routing. | Potential lateral movement of corporate malware directly into factory SCADA. | RSK-OT-002 | Critical | Remove direct RDP firewall rule; enforce Claroty SRA Jump Host with MFA. | Management agrees; firewall team will remove direct route by Aug 31. | Network Security Lead | 2026-08-31 | In Progress
AUD-007 | Unpatched Legacy OS Machine | NIST SP 800-82 Rev 3 §6.2 | Windows 7 Embedded operating system on Pune Gear Shaping Machine lacks MS17-010 patch. | Machine cannot be upgraded without replacing physical CNC controller hardware ($1.2M cost). | Exposes Line A to EternalBlue ransomware propagation. | RSK-OT-001 | Critical | Implement IDMZ micro-segmentation, USB lockout, and schedule upgrade during Q4 overhaul. | Management accepts temporary risk under RA-2026-001; compensating controls deployed. | Pune Plant Manager & OT Lead | 2026-11-30 | Risk Accepted
AUD-008 | Vendor Remote Access Governance | ISO 27001:2022 A.5.19 | Third-party vendors accessing factory PLCs via unmonitored legacy SSL VPN without MFA. | Contract agreements lacked mandatory MFA and session recording requirements. | Unauthorized vendor access or credential theft leading to undetected PLC manipulation. | RSK-OT-003 | Critical | Mandate Claroty SRA jump-host portal with Duo MFA and full session recording. | Deploying Claroty SRA portal across all 6 plants; completion targeted Sept 15. | Third-Party Risk Manager | 2026-09-15 | In Progress
AUD-009 | Dormant Privileged Accounts | NIST CSF PR.AC-1 | 12 Active Directory domain admin accounts inactive for >90 days without deactivation. | Lack of automated identity lifecycle reconciliation between HR and AD. | Increased attack surface for brute-force credential stuffing attacks. | RSK-IT-003 | High | Disable dormant accounts immediately and implement automated 90-day AD cleanup script. | Accounts disabled immediately; automated cleanup script deployed in staging. | IAM Operations Lead | 2026-08-20 | Closed
AUD-010 | Unrestricted USB Devices on EWS | NIST SP 800-82 Rev 3 §6.4 | Engineering Workstations in Nagpur Plant allow read/write access to unverified personal USB drives. | Group Policy USB block not linked to local plant Active Directory OUs. | High risk of malware infection (e.g., Stuxnet/W32.Shty) via technician USB drives. | RSK-OT-006 | High | Enforce physical port locks and GPO USB block; install optical USB scan kiosk. | Installing physical USB locks; GPO updated across all plant OUs. | Plant IT Supervisor | 2026-08-30 | In Progress
AUD-011 | OT Network Segmentation | IEC 62443-3-3 SR 5.1 | Direct RDP connection permitted from Corporate IT laptop to Level 2 WinCC SCADA HMI in Pune Plant. | Legacy firewall rule left active without IDMZ jump host routing. | Potential lateral movement of corporate malware directly into factory SCADA. | RSK-OT-002 | Critical | Remove direct RDP firewall rule; enforce Claroty SRA Jump Host with MFA. | Management agrees; firewall team will remove direct route by Aug 31. | Network Security Lead | 2026-08-31 | In Progress
AUD-012 | Unpatched Legacy OS Machine | NIST SP 800-82 Rev 3 §6.2 | Windows 7 Embedded operating system on Pune Gear Shaping Machine lacks MS17-010 patch. | Machine cannot be upgraded without replacing physical CNC controller hardware ($1.2M cost). | Exposes Line A to EternalBlue ransomware propagation. | RSK-OT-001 | Critical | Implement IDMZ micro-segmentation, USB lockout, and schedule upgrade during Q4 overhaul. | Management accepts temporary risk under RA-2026-001; compensating controls deployed. | Pune Plant Manager & OT Lead | 2026-11-30 | Risk Accepted
AUD-013 | Vendor Remote Access Governance | ISO 27001:2022 A.5.19 | Third-party vendors accessing factory PLCs via unmonitored legacy SSL VPN without MFA. | Contract agreements lacked mandatory MFA and session recording requirements. | Unauthorized vendor access or credential theft leading to undetected PLC manipulation. | RSK-OT-003 | Critical | Mandate Claroty SRA jump-host portal with Duo MFA and full session recording. | Deploying Claroty SRA portal across all 6 plants; completion targeted Sept 15. | Third-Party Risk Manager | 2026-09-15 | In Progress
AUD-014 | Dormant Privileged Accounts | NIST CSF PR.AC-1 | 12 Active Directory domain admin accounts inactive for >90 days without deactivation. | Lack of automated identity lifecycle reconciliation between HR and AD. | Increased attack surface for brute-force credential stuffing attacks. | RSK-IT-003 | High | Disable dormant accounts immediately and implement automated 90-day AD cleanup script. | Accounts disabled immediately; automated cleanup script deployed in staging. | IAM Operations Lead | 2026-08-20 | Closed
AUD-015 | Unrestricted USB Devices on EWS | NIST SP 800-82 Rev 3 §6.4 | Engineering Workstations in Nagpur Plant allow read/write access to unverified personal USB drives. | Group Policy USB block not linked to local plant Active Directory OUs. | High risk of malware infection (e.g., Stuxnet/W32.Shty) via technician USB drives. | RSK-OT-006 | High | Enforce physical port locks and GPO USB block; install optical USB scan kiosk. | Installing physical USB locks; GPO updated across all plant OUs. | Plant IT Supervisor | 2026-08-30 | In Progress
AUD-016 | OT Network Segmentation | IEC 62443-3-3 SR 5.1 | Direct RDP connection permitted from Corporate IT laptop to Level 2 WinCC SCADA HMI in Pune Plant. | Legacy firewall rule left active without IDMZ jump host routing. | Potential lateral movement of corporate malware directly into factory SCADA. | RSK-OT-002 | Critical | Remove direct RDP firewall rule; enforce Claroty SRA Jump Host with MFA. | Management agrees; firewall team will remove direct route by Aug 31. | Network Security Lead | 2026-08-31 | In Progress
AUD-017 | Unpatched Legacy OS Machine | NIST SP 800-82 Rev 3 §6.2 | Windows 7 Embedded operating system on Pune Gear Shaping Machine lacks MS17-010 patch. | Machine cannot be upgraded without replacing physical CNC controller hardware ($1.2M cost). | Exposes Line A to EternalBlue ransomware propagation. | RSK-OT-001 | Critical | Implement IDMZ micro-segmentation, USB lockout, and schedule upgrade during Q4 overhaul. | Management accepts temporary risk under RA-2026-001; compensating controls deployed. | Pune Plant Manager & OT Lead | 2026-11-30 | Risk Accepted
AUD-018 | Vendor Remote Access Governance | ISO 27001:2022 A.5.19 | Third-party vendors accessing factory PLCs via unmonitored legacy SSL VPN without MFA. | Contract agreements lacked mandatory MFA and session recording requirements. | Unauthorized vendor access or credential theft leading to undetected PLC manipulation. | RSK-OT-003 | Critical | Mandate Claroty SRA jump-host portal with Duo MFA and full session recording. | Deploying Claroty SRA portal across all 6 plants; completion targeted Sept 15. | Third-Party Risk Manager | 2026-09-15 | In Progress
AUD-019 | Dormant Privileged Accounts | NIST CSF PR.AC-1 | 12 Active Directory domain admin accounts inactive for >90 days without deactivation. | Lack of automated identity lifecycle reconciliation between HR and AD. | Increased attack surface for brute-force credential stuffing attacks. | RSK-IT-003 | High | Disable dormant accounts immediately and implement automated 90-day AD cleanup script. | Accounts disabled immediately; automated cleanup script deployed in staging. | IAM Operations Lead | 2026-08-20 | Closed
AUD-020 | Unrestricted USB Devices on EWS | NIST SP 800-82 Rev 3 §6.4 | Engineering Workstations in Nagpur Plant allow read/write access to unverified personal USB drives. | Group Policy USB block not linked to local plant Active Directory OUs. | High risk of malware infection (e.g., Stuxnet/W32.Shty) via technician USB drives. | RSK-OT-006 | High | Enforce physical port locks and GPO USB block; install optical USB scan kiosk. | Installing physical USB locks; GPO updated across all plant OUs. | Plant IT Supervisor | 2026-08-30 | In Progress
AUD-021 | OT Network Segmentation | IEC 62443-3-3 SR 5.1 | Direct RDP connection permitted from Corporate IT laptop to Level 2 WinCC SCADA HMI in Pune Plant. | Legacy firewall rule left active without IDMZ jump host routing. | Potential lateral movement of corporate malware directly into factory SCADA. | RSK-OT-002 | Critical | Remove direct RDP firewall rule; enforce Claroty SRA Jump Host with MFA. | Management agrees; firewall team will remove direct route by Aug 31. | Network Security Lead | 2026-08-31 | In Progress
AUD-022 | Unpatched Legacy OS Machine | NIST SP 800-82 Rev 3 §6.2 | Windows 7 Embedded operating system on Pune Gear Shaping Machine lacks MS17-010 patch. | Machine cannot be upgraded without replacing physical CNC controller hardware ($1.2M cost). | Exposes Line A to EternalBlue ransomware propagation. | RSK-OT-001 | Critical | Implement IDMZ micro-segmentation, USB lockout, and schedule upgrade during Q4 overhaul. | Management accepts temporary risk under RA-2026-001; compensating controls deployed. | Pune Plant Manager & OT Lead | 2026-11-30 | Risk Accepted
AUD-023 | Vendor Remote Access Governance | ISO 27001:2022 A.5.19 | Third-party vendors accessing factory PLCs via unmonitored legacy SSL VPN without MFA. | Contract agreements lacked mandatory MFA and session recording requirements. | Unauthorized vendor access or credential theft leading to undetected PLC manipulation. | RSK-OT-003 | Critical | Mandate Claroty SRA jump-host portal with Duo MFA and full session recording. | Deploying Claroty SRA portal across all 6 plants; completion targeted Sept 15. | Third-Party Risk Manager | 2026-09-15 | In Progress
AUD-024 | Dormant Privileged Accounts | NIST CSF PR.AC-1 | 12 Active Directory domain admin accounts inactive for >90 days without deactivation. | Lack of automated identity lifecycle reconciliation between HR and AD. | Increased attack surface for brute-force credential stuffing attacks. | RSK-IT-003 | High | Disable dormant accounts immediately and implement automated 90-day AD cleanup script. | Accounts disabled immediately; automated cleanup script deployed in staging. | IAM Operations Lead | 2026-08-20 | Closed
AUD-025 | Unrestricted USB Devices on EWS | NIST SP 800-82 Rev 3 §6.4 | Engineering Workstations in Nagpur Plant allow read/write access to unverified personal USB drives. | Group Policy USB block not linked to local plant Active Directory OUs. | High risk of malware infection (e.g., Stuxnet/W32.Shty) via technician USB drives. | RSK-OT-006 | High | Enforce physical port locks and GPO USB block; install optical USB scan kiosk. | Installing physical USB locks; GPO updated across all plant OUs. | Plant IT Supervisor | 2026-08-30 | In Progress
AUD-026 | OT Network Segmentation | IEC 62443-3-3 SR 5.1 | Direct RDP connection permitted from Corporate IT laptop to Level 2 WinCC SCADA HMI in Pune Plant. | Legacy firewall rule left active without IDMZ jump host routing. | Potential lateral movement of corporate malware directly into factory SCADA. | RSK-OT-002 | Critical | Remove direct RDP firewall rule; enforce Claroty SRA Jump Host with MFA. | Management agrees; firewall team will remove direct route by Aug 31. | Network Security Lead | 2026-08-31 | In Progress
AUD-027 | Unpatched Legacy OS Machine | NIST SP 800-82 Rev 3 §6.2 | Windows 7 Embedded operating system on Pune Gear Shaping Machine lacks MS17-010 patch. | Machine cannot be upgraded without replacing physical CNC controller hardware ($1.2M cost). | Exposes Line A to EternalBlue ransomware propagation. | RSK-OT-001 | Critical | Implement IDMZ micro-segmentation, USB lockout, and schedule upgrade during Q4 overhaul. | Management accepts temporary risk under RA-2026-001; compensating controls deployed. | Pune Plant Manager & OT Lead | 2026-11-30 | Risk Accepted
AUD-028 | Vendor Remote Access Governance | ISO 27001:2022 A.5.19 | Third-party vendors accessing factory PLCs via unmonitored legacy SSL VPN without MFA. | Contract agreements lacked mandatory MFA and session recording requirements. | Unauthorized vendor access or credential theft leading to undetected PLC manipulation. | RSK-OT-003 | Critical | Mandate Claroty SRA jump-host portal with Duo MFA and full session recording. | Deploying Claroty SRA portal across all 6 plants; completion targeted Sept 15. | Third-Party Risk Manager | 2026-09-15 | In Progress
AUD-029 | Dormant Privileged Accounts | NIST CSF PR.AC-1 | 12 Active Directory domain admin accounts inactive for >90 days without deactivation. | Lack of automated identity lifecycle reconciliation between HR and AD. | Increased attack surface for brute-force credential stuffing attacks. | RSK-IT-003 | High | Disable dormant accounts immediately and implement automated 90-day AD cleanup script. | Accounts disabled immediately; automated cleanup script deployed in staging. | IAM Operations Lead | 2026-08-20 | Closed
AUD-030 | Unrestricted USB Devices on EWS | NIST SP 800-82 Rev 3 §6.4 | Engineering Workstations in Nagpur Plant allow read/write access to unverified personal USB drives. | Group Policy USB block not linked to local plant Active Directory OUs. | High risk of malware infection (e.g., Stuxnet/W32.Shty) via technician USB drives. | RSK-OT-006 | High | Enforce physical port locks and GPO USB block; install optical USB scan kiosk. | Installing physical USB locks; GPO updated across all plant OUs. | Plant IT Supervisor | 2026-08-30 | In Progress